## Progress
Rebuild DMS
Function | For | View, API | Name | Controller | Progress
User & Login | For User | View | Login
User & Login | For User | View | Reset PW |  | OK
User & Login | For User | View | Create New Acc |  | OK
User & Login | For User | View | Change PW |  | OK
User & Login | For User | View | Change Profile |  | OK
User & Login | For User | API | api_login |  | OK
User & Login | For User | API | api_getUserData |  | OK
User & Login | For User | API | api_getRoleCategory |  | OK
User & Login | For User | API | api_getGradeCategory |  | OK
User & Login | For User | API | api_getListDept |  | OK
User & Login | For User | API | api_changePW |  | OK | update lai phan tren office
User & Login | For User | API | api_changeUserProfile |  | OK
User & Login | For User | API | api_resetPassword |  | OK
User & Login | For User | API | api_createNewAccount |  | OK
User & Login | For User | API | api_sendEmailResetPW |  | Pending
User & Login | For User | API | api_getDeptCategory |  | OK
User & Login | For Admin | View | List Users |  | OK
User & Login | For Admin | View | Detail user & verify users |  | OK
User & Login | For Admin | API | api_getListUsers | Authen | OK | chu ý phân trang
User & Login | For Admin | API | api_getUserProfileByID | Authen | OK
User & Login | For Admin | API | api_changeOrAddRoleForUser | Authen | OK
User & Login | For Admin | API | api_getListDept |  | Pending | Chua can thiet
User & Login | For Admin | API | api_getDetailDept |  | Pending | Chua can thiet
User & Login | For Admin | API | api_addDept |  | Pending | Chua can thiet
User & Login | For Admin | API | api_editDept |  | Pending | Chua can thiet
User & Login | For Admin | API | api_suggestRole |  | Pending | Chua can thiet
MR | For User | View | Chart progress |  | OK | Update lai sau khi co api chinh thuc
MR | For User | View | Seaching |  | OK
MR | For User | View | Show btn function theo role |  | OK
MR | For User | view | Show table |  | OK
MR | For User | view | Show detail MR |  | doing
MR | For User | view | page issue MR |  | OK
MR | For User
MR | For User
MR | For User
MR | For User
MR | For User
MR | For User | API | api_getMRList | MR_API | OK
MR | For User | API | api_getSumarizeMRPending | MR_API | OK
MR | For User |  | api_issueMR | MR_API | Pending
MR | For User
Die | For user | View | show list die |  | OK
Die |  | View | Show all |  | OK
Die |  | API | api_getDieList | DIE_API | OK | by search and show all
Die |  | API | api_GetModelList | CommonAPI | OK
Die |  | View | search die,part, model, supplier, name |  | OK
Die |  | View | Add new die |  | OK | Chưa có dowload form
Die |  | API | Add new die | DIE_API | OK | bao gồm cả add die by MR (chưa test MR)
Die |  | API | Add new die by List excel | DIE_API | Pending | Tận dụng controller common đã làm ở cty
Die |  | API | GenarateAndUpdateNewDie | CommonFunction | OK | Manual Add & MR/PO added Common/Family MR add common
Die |  | API | api_DownloadListDie | DIE_API | Pending | Tận dụng controller common đã làm ở cty
Die |  | API | api_uploadListDie(edit) | DIE_API | No Doing | Ko thuc hien vi co the lam loi database hang loat
Die |  | View | Upload list die (Edit) |  | No Doing | Ko thuc hien vi co the lam loi database hang loat
Die |  | View | Show die detail |  | OK
Die |  | API | api_getDieDetail | DIE_API | OK
|  | sql function | genarateDieScore |  | OK
Die |  | API | api_getDieScore | DIE_API | OK | Xem lai concept 90%
|  | View | Die_score chart |  | OK
Die |  | View | Edit/Update die information |  | OK
Die |  | API | api_updateDieInfo | DIE_API | OK
Die |  | View | Chart die |  | OK | bao gồ cả search khi click on chart
|  | API | api_getSumarizeDieFollowing | DIE_API | OK
|  | sql function | genarateDiePendingStatus |  | OK
|  | sql function | Trigger khi có update trên table die thì update lại die progress |  | OK
|  | sql function | Trigger khi có update trên table MR thì update lại die progress |  | OK
|  | sql function | Trigger khi có update trên table PO thì update lại die progress |  | OK
|  | sql function | Trigger khi có update trên table DSUM thì update lại die progress |  | OK
|  | View | Add/Edit common die |  | OK
|  | API | api_edit_add_delete_commondie |  | OK | Delete hẳn common trong bang common die
|  | API | Delete die |  | OK
|  | View | View update check die result |  | OK | OK
|  | API | Api_check die result |  | Pending | Xem lai phan post file report nhung control ko nhan duoc
|  |  | goto detail each item |  | Pending | Sau khi cac function xay dung xong

## convert database
1 | Khi convert MR type thi phai sua lai toan bo type_ID cua MR cu
9/29/2024 đã thay đổi unique contain của bảng Common_die (part_id, die_id) 9/29/2024: đã xóa những common bị trùng (part_id, die_id)
9/30/2024 đã thay đổi unique của part và dies Đã xóa dữ liệu trùng

## C#
Thư viện sử dụng |  | Ver
1 | Net6.0 | 6
2 | Npgsql | 8.0.3 | kết nối đến database postgress
Microsoft.AspNetCore.Authentication.Cookies
Update lại File style.css từ dòng 1142 => 1180

## Sheet1
Loại | Loại | Componet | Common | Family | Case 1: | ` | OK
New | 11A | 1 | Ko | ko | case2: | Loại 21AComponet1Common KoFamilyko | OK
Addition | 21A | 3 | RC5-1234 | RC6-0000 |  | Loại 12AComponet1Common KoFamilyko | OK
Renew | 12A |  | RC5-1234-00 | RC6-0001-000 |  | Loại 13AComponet1Common KoFamilyko | OK
Renew | 13A |  | RC5-1234-000 |  |  | Loại 14AComponet1Common KoFamilyko | OK
Renew | 14A |  | RC5-3457-000 |  |  | Loại 18AComponet1Common KoFamilyko | OK
X5 | 15A |  | FE3-1243
X6 | 16A |  |  |  |  | Loại 11AComponet3Common KoFamilyko | OK
X7 | 17A |  |  |  |  | Loại 11AComponet3Common RC5-1234Familyko | OK
X8 | 18A |  |  |  |  | Loại 11AComponet3Common RC5-1234-00Familyko | OK
X9 | 19A |  |  |  |  | Loại 11AComponet3Common RC5-1234-00FamilyRC6-0000 | OK
[6 empty] | Loại 15AComponet1Common FE3-1243FamilyRC6-0001-000 | OK

## Sheet2
condition_id | factor_id | condition_name | condition_from | condition_less_than | subtract_score | explain
1 | 1 | Not Yet Repair | -1 | 0 | 0
2 | 1 | Repair fee < 20% | 0 | 20 | -2
3 | 1 | 20% ≤ Repair Fee < 40% | 20 | 40 | -4
4 | 1 | 40% ≤ Repair Fee < 60% | 40 | 60 | -6
5 | 1 | 60% ≤ Repair Fee < 80% | 60 | 80 | -8
6 | 1 | Repair Fee ≥ 80% | 80 | 1000000 | -10
7 | 2 | Life < 80% | 0 | 80 | 0
8 | 2 | 80% ≤ Life < 120% | 80 | 120 | -5
9 | 2 | Life ≥ 120% | 120 | 1000000 | -10
10 | 3 | Target < 80% | 0 | 80 | 0
11 | 3 | 80% ≤ Target < 120% | 80 | 120 | -5
12 | 3 | Target ≥ 120% | 120 | 1000000 | -10
13 | 4 | Not Yet Transfer | -1 | 0 | 0
14 | 4 | To Or Current Inhouse | 0 | 1 | 10
15 | 4 | To Out Side | 1 | 2 | -10
16 | 5 | NY OH But under target | -2 | -1 | 0
17 | 5 | NY OH But over target | -1 | 0 | -10
18 | 5 | OH Less 1 year | 0 | 1 | 10
19 | 5 | OH less 2 year | 1 | 2 | 6
20 | 5 | OH less 3 year | 2 | 3 | 3
21 | 5 | OH over 3 year | 3 | 1000000 | 0
22 | 6 | Extend < 200K | 0 | 200 | 0
23 | 6 | 200K ≤ Extend < 400K | 200 | 400 | -2
24 | 6 | 400K ≤ Extend < 600K | 400 | 600 | -4
25 | 6 | 600K ≤ Extend < 800K | 600 | 800 | -6
26 | 6 | Extend ≥ 800K | 800 | 1000000 | -10
27 | 7 | Lack | -1 | 0 | -10
28 | 7 | Enough | 0 | 1 | 0
29 | 7 | Surplus | 1 | 2 | 10
30 | 8 | Repair NG point | -1 | 0 | -5
31 | 8 | OK/ Review No Check | 0 | 1 | 0
32 | 8 | Need Renew | 1 | 2 | -10

## Sheet3
Tính die demand
| Total demand | 1000 | total Cap | 1401 | die need | 0.71378
Thừa
| Cap 1 | 400 | 401 | TRUE
| Cap 2 | 600 | 401 | FALSE
| Cap 2 | 401 | 401 | FALSE