## Progress
Rebuild DMS |  |  |  | Controller
User & Login | For User | View | Login
User & Login | For User | View | Reset PW |  | OK
User & Login | For User | View | Create New Acc |  | OK
User & Login | For User | View | Change PW |  | OK
User & Login | For User | View | Change Profile |  | OK
User & Login | For User | API | api_login |  | OK
User & Login | For User | API | api_getUserData |  | OK
User & Login | For User | API | api_getRoleCategory |  | OK
User & Login | For User | API | api_getGradeCategory |  | OK
User & Login | For User | API | api_getListDept |  | OK
User & Login | For User | API | api_changePW |  | OK | update lai phan tren office
User & Login | For User | API | api_changeUserProfile |  | OK
User & Login | For User | API | api_resetPassword |  | OK
User & Login | For User | API | api_createNewAccount |  | OK
User & Login | For User | API | api_sendEmailResetPW |  | Pending
User & Login | For User | API | api_getDeptCategory |  | OK
User & Login | For Admin | View | List Users |  | OK
User & Login | For Admin | View | Detail user & verify users |  | OK
User & Login | For Admin | API | api_getListUsers | Authen | OK
User & Login | For Admin | API | api_getUserProfileByID | Authen | OK
User & Login | For Admin | API | api_changeOrAddRoleForUser | Authen | OK
User & Login | For Admin | API | api_getListDept |  | Pending | Chua can thiet
User & Login | For Admin | API | api_getDetailDept |  | Pending | Chua can thiet
User & Login | For Admin | API | api_addDept |  | Pending | Chua can thiet
User & Login | For Admin | API | api_editDept |  | Pending | Chua can thiet
User & Login | For Admin | API | api_suggestRole |  | Pending | Chua can thiet
MR | For User | View | Chart progress |  | OK
MR | For User | View | Seaching |  | OK
MR | For User | View | Show btn function theo role |  | OK
MR | For User | View | Show table |  | OK
MR | For User | View | Show detail MR |  | OK
MR | For User | View | page issue MR |  | OK | Linh to ECN, Link to DSUM, Link to TPI, Warning…
MR | For User | View | Check MR PAE |  | OK | OK for 1by1 and mutil
MR | For User | View | Check MR PLAN |  | OK | OK for 1by1 and mutil
MR | For User | View | Check MR PUR |  | OK | OK for 1by1 and mutil
MR | For User | View | Approve MR PAE |  | OK | OK for 1by1 and mutil
MR | For User | View | Approve MR PE1 |  | OK | OK for 1by1 and mutil
MR | For User | View | Approve MR CRG |  | OK | OK for 1by1 and mutil
MR | For User | View | Approve MR PLAN |  | OK | OK for 1by1 and mutil
MR | For User | View | Approve MR PUR |  | OK | OK for 1by1 and mutil
MR | For User | API | api_rejectMR | MR_API | OK
MR | For User | API | api_checkAndApproveMR | MR_API | OK
MR | For User | API | api_getMRList | MR_API | OK
MR | For User | API | api_getSumarizeMRPending | MR_API | OK
MR | For User | API | api_issueMR | MR_API | OK | Add thêm "GenarateNewDie" when Die controller(H) import
MR | For User | API | api_issueMRByExcel | MR_API | OK
MR | For User | API | Download MR form | MR_API | OK
MR | For User | View | DEPT & role Nào thì show pending item của người đó |  | OK
MR | For User | View | Show all MR |  | OK
MR | For User | API | Download List MR | MR_API | OK
|  | API | api_updateListBudgetCode |  | Pending
|  | View | View Plan update budget code list |  | Pending
|  | API | api_createExchangeRate | MR_API | Pending
|  | View | View show exchage rate |  | Pending
|  |  | Chuyển tiếp từ MR => PO |  | OK
PO | For User | View | Chart progress |  | OK | Bao gồm cả click to show
PO | For User | View | Seaching |  | OK | Bao gồm showall
PO | For User | View | Show btn function theo role |  | OK
PO | For User | View | Show table |  | OK
PO | For User | View | Show detail PO New |  | OK
PO | For User | View | Show detail PO Change |  | OK
PO | For User | View | Show detail PO Cancel |  | OK
PO | For User | View | page issue PO |  | OK
PO | For User | API | api_issueNewPO |  | OK | 2024-11-15
PO | Send Email | API | send email to GM when tempo issue |  | Pending
PO | For User | View | Request Change 1 by 1 |  | OK | 2024-11-15
PO | For User | View | Request Change by Excel |  | Pending | Make same function upload file
PO | For User | API | api_changePORequest |  | OK | 2024-11-15
PO | For User | View | Request Cancel 1 by 1 |  | OK | 2024-11-15
PO | For User | View | Request Cancel by Excel |  | Pending | Make same function upload file
PO | For User | API | api_cancelPORequest |  | OK | 2024-11-15
|  | API | api_change_cancel_by_excel |  | Pending
PO | For User | View | Apporve PO PUR(M1/GM), PUS, PUR app NPIS
PO | For User |  | PUC INPUT NIPIS
PO | For User |  | PUC DOUBL Check
PO | For User |  | PUS Input price
PO | For User | View | download list PO
PO | For User | View | download PUC new
PO | For User | View | Download PUC CH&&CC
PO | For User | View | Upload price
PO | For User | View | Upload payment

## convert database
1 | Khi convert MR type thi phai sua lai toan bo type_ID cua MR cu
2 | Khi cover database các file attach file xử lí full part /File/Attachment/MR/….xlsx
3 | Đã sửa đổi 2 function getMR và searchMR nên cần cập nhật lại ở H | ĐÃ cập nhật 11/8/2024
4 | Can update lai bang PO_category va function sumMR va sumPO
F đã cập nhật lài function search PO (loại bỏ p_status paramater) chuyển vào p_search

## C#
Thư viện sử dụng |  | Ver
1 | Net6.0 | 6
2 | Npgsql | 8.0.3 | kết nối đến database postgress
Microsoft.AspNetCore.Authentication.Cookies